RESPONSE TO REQUEST FOR PROPOSAL

Cloud Migration & Platform Modernisation Services

Submitted to:  NexaRetail Pvt Ltd, Mumbai

Submitted by:  Dexter Corp Pvt Ltd, Chennai

Date:  March 15, 2026

Proposal Ref:  DXC-2026-NXR-001

Validity:  30 days from submission date

# 1. Executive Summary

Dexter Corp is pleased to respond to NexaRetail's Request for Proposal for the migration of their legacy on-premise retail management platform to AWS and the modernisation of three core monolithic services into a microservices architecture.

We propose a phased 18-month engagement valued at ₹85,00,000 (INR). Based on our recently completed Cloud Migration engagement for RetailMart India (₹1.1 Crore, 2023–2024) — a directly comparable retail platform — we are confident in our ability to deliver on time and within budget.

Dexter Corp has been building enterprise software since April 2022. In under 4 years, we have delivered 6 completed projects with a 100% on-time record, and our current ARR of ₹23.7 Crore (March 2026) reflects the trust our clients place in our delivery.

# 2. Understanding of Requirements

Based on the RFP and our discovery call with Deepa Menon (CTO, NexaRetail) on March 5, 2026, we understand the following key requirements:

| # | Requirement | Our Approach |
| --- | --- | --- |
| 1 | Migrate legacy Oracle DB (400GB) to AWS RDS | Database migration using AWS DMS with parallel-run validation period |
| 2 | Re-architect 3 monolithic services | Strangler Fig pattern — incremental decomposition, zero big-bang risk |
| 3 | Zero-downtime migration | Blue-green deployments + feature flags for all production cutover events |
| 4 | Real-time analytics dashboard | React frontend + AWS Redshift + daily ETL via Apache Airflow |
| 5 | CI/CD pipeline setup | GitHub Actions + AWS CodeDeploy + automated testing gate at every stage |

# 3. Proposed Solution & Phases

## Phase 1 — Assessment & Blueprint (Months 1–2)

• Infrastructure audit: inventory of 22 identified on-premise services

• Dependency mapping using AWS Application Discovery Service

• Target architecture design document (approved by NexaRetail CTO)

• Risk register and mitigation plan

• Deliverable: Cloud Migration Blueprint — sign-off required before Phase 2

## Phase 2 — Foundation & Lift-and-Shift (Months 3–9)

• AWS Landing Zone: VPC, IAM roles, S3, CloudFront, Route53 setup

• Database migration: Oracle → PostgreSQL 16 on AWS RDS Multi-AZ

• Lift-and-shift of 16 non-critical services via AWS DMS

• CI/CD pipeline: GitHub Actions → ECR → ECS Fargate

• Milestone: All non-critical services live on AWS; Oracle decommissioned

## Phase 3 — Microservices Modernisation (Months 10–16)

• Re-architect: Inventory Service, Order Management Service, Customer Service

• API Gateway layer (AWS API Gateway + custom request routing)

• Event-driven communication via Amazon SQS between services

• Real-time analytics: Redshift + Airflow ETL + React dashboard

• Load testing: 10,000 concurrent users simulation using Locust

## Phase 4 — Stabilisation & Handover (Months 17–18)

• Performance optimisation and cost right-sizing

• Full documentation: runbooks, architecture diagrams, DR playbook

• Team knowledge transfer (3 sessions with NexaRetail engineering team)

• 3-month hypercare support post-handover at no additional cost

# 4. Proposed Team

| Role | Name | Experience | Allocation |
| --- | --- | --- | --- |
| Engagement Lead | Karthik Suresh (CEO) | 14 years | 20% (oversight) |
| Project Manager | Lavanya Iyer (Sr PM) | 10 years | 100% |
| Cloud Architect | Meena Krishnan (Lead) | 8 years | 100% |
| Cloud Engineer | Akash Verma | 4 years | 100% |
| Backend Engineer | Arun Krishnamurthy | 6 years | 100% |
| Backend Engineer | Kavya Reddy | 3 years | 100% |
| Frontend Engineer | Vivek Pillai (Sr) | 8 years | 60% |
| QA Lead | Anil Kumar | 8 years | 60% |
| Data Engineer | Deepak Ghosh | 4 years | 60% |

# 5. Commercial Proposal

| Item | Details |
| --- | --- |
| Total Engagement Value | ₹85,00,000 (INR) exclusive of GST |
| Phase 1 — Assessment | ₹8,00,000 — payable on contract signing |
| Phase 2 — Foundation | ₹32,00,000 — payable on Phase 2 completion |
| Phase 3 — Modernisation | ₹35,00,000 — payable on Phase 3 completion |
| Phase 4 — Stabilisation | ₹10,00,000 — payable on final sign-off |
| Post-Delivery AMC (Optional) | ₹12,75,000/year (15% of project value) |
| Payment Terms | Net 30 from invoice date |
| Validity of Proposal | 30 days from March 15, 2026 |

# 6. Why Dexter Corp

• Directly comparable delivered project: RetailMart India cloud migration (₹1.1 Crore, on time)

• AWS Advanced Consulting Partner with certified architects

• 4 years of enterprise delivery — 12 active clients, 6 completed projects, 0 missed deadlines

• Entire delivery team is in Chennai — no offshore handoffs, no timezone gaps

• Client NPS: 74 (as of Q4 FY25-26)

• 3-month hypercare included — no additional cost

Dexter Corp Pvt Ltd  |  4th Floor, Prestige Tech Park, OMR, Chennai – 600119

contact@dextercorp.in  |  +91 44 4567 8901  |  www.dextercorp.in